VOLUME 2

SECTION 3 SPECIAL CONDITIONS FOR EUROPEAN UNION EXTERNAL ACTIONS

# CONTENTS

# These conditions amplify and supplement the general conditions governing the contract. Unless the special conditions provide otherwise, the general conditions remain fully applicable. The numbering of the articles of the special conditions is not consecutive but follows the numbering of the general conditions. Exceptionally, and with the approval of the competent European Commission departments, other clauses can be indicated to cover particular situations.

# Contract value

# The contracting authority hereby agrees to pay to the contractor, in consideration of the execution and completion of the works and remedying of defects therein, the amount of the contract value mentioned in article 2 of the Main Conditions or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the contract. VAT will be paid in compliance with the binding regulations, national law and international agreements concerning the execution of the project.

# The amount of the contract value mentioned in article 2 of the Main Conditions shall be composed of:

- Contract price (excluding VAT) RSD [insert amount (insert amount in words)].

# Order of precedence of contract documents

The following documents shall be deemed to form and be read and construed as part of this contract, in the following order of precedence:

- The main conditions

- the special conditions,

- the general conditions,

- the bill of quantities (after arithmetical corrections) and detailed breakdown of prices,

- the technical and/or performance specifications,

- the design documentation (drawings),

- the tender,

- any other documents forming part of the contract.

The various documents making up the contract shall be deemed to be mutually explanatory; in cases of ambiguity or divergence, they shall prevail in the order in which they appear above. Addenda shall have the order of precedence of the document they are amending.

Article 2	Language of the contract

2.1	The language used shall be English.

Article 4	Communication

4.1	Any written communication related to this Contract between the Contracting Authority on the one hand and the Contractor on the other hand, must state the Contract title and contract number and must be sent by post, fax, e-mail or by hand to the following addresses:

For the Contracting Authority:

| Name: |  |
| --- | --- |
| Contact Person: |  |
| Address: |  |
| Telephone: |  |
| E-mail: |  |

For the Contractor:

| Name: |  |
| --- | --- |
| Contact Person: |  |
| Address: |  |
| Telephone: |  |
| E-mail: |  |

For the Supervisor:

| Name: |  |
| --- | --- |
| Contact Person: |  |
| Address: |  |
| Telephone: |  |
| E-mail: |  |

E-mail communications between the parties are also permitted, in particular for communications between the Supervisor and the Contractor. Formal notifications, such as notifications of termination or breach or notifications which have an impact on Contract Price or additional cost claims must be submitted through the methods mentioned above. Email may be used as a supplementary notification method for such formal notifications.

Where signed documents are transmitted electronically they shall be confirmed by delivery of hard copy with the original signatures within one week.

4.4	Communication via electronic exchange system (EES)

Not applicable

4.5 & 4.6 	Mail or email communication

If communications through the Portal have not been activated or a certain type of communication is not yet supported by the Portal, communications will be sent via email, or, exceptionally, on paper, via mail services, to the following addresses, until communications via the Portal are activated.

For the purpose of this contract, mail or email communications must be sent to the following addresses:

Contracting authority:

[Full name]

[Full official address]

[Email: [complete]] ]

Contractor (or leader in the case of a joint tender):

[Full name]

[Function]

[Company name]

[Full official address]

Email: [complete]

Article 5	Supervisor and supervisor’s representative

5.2	The name and address of the Supervisor and his Representative(s) shall be given to the Contractor after the award of the Contract.

The Contracting Authority shall appoint a Supervisor to carry out duties referred to in the Contract. The Supervisor may have further staff to which he delegates matters related to the Contract.

5.3	The Supervisor acts for the Contracting Authority. He has no authority to relieve either party of any duties, obligations or responsibilities under the Contract or to amend the Contract.

Any approval, check, certificate, consent, examination, inspection, instruction, notice, proposal, request, test, or similar act by the Supervisor (including absence or disapproval) shall not relieve the Contractor from any responsibility he has under the Contract, including the responsibility for errors, omissions, discrepancies and non-compliances.

Any failure to disapprove any work, plant or materials shall not constitute approval, and shall therefore not prejudice the right of the Supervisor to reject the work, plant or materials.

The Supervisor may issue to the Contractor (at any time) instructions which may be necessary for the execution of the works and the remedying of any defects, all in accordance with the Contract. The Contractor shall only take instructions from the Supervisor. If an instruction constitutes a modification, Article 37 of General Conditions shall apply.

The Supervisor shall consult with each party in an endeavour to reach agreement. If agreement is not achieved, the Supervisor shall make a fair determination in accordance with the Contract, taking due regard of all relevant circumstances.

5.4	The Supervisor shall obtain the written approval of the Contracting Authority prior taking any of the following actions specified in the General Conditions:

(a)	Approve any extension of time determined under Article 35 of the General 		Conditions;

(b)	Approve any modification of the Contract and/or issuing any administrative 		order under Article 37 of the General Conditions.

Administrative orders issued by the Supervisor shall be dated, numbered and entered in a register. The Supervisor shall send them electronically (by email) to representatives of the Contractor, of the Beneficiary and of the Contracting Authority. Hard copies shall be delivered by hand to representatives of the Contractor and of the Beneficiary, and where appropriate, also to the representative of the Contracting Authority.

Article 8	Documents to be provided

8.1	The Supervisor’s approval of any technical documentation shall not relieve the Contractor of his responsibilities under the Contract.

The Contractor should maintain manuals as work diary together with proposed or changed drawings during the permanent work in a format and manner approved by the Supervisor.

The Contractor shall be responsible for the safekeeping of any formal documents relating to the Works.

Article 9	Access to the site

There is no a derogation from Article 9 of the GC.

Article 12	General obligations

12.9	The visibility measures must comply with the rules laid down in the Communication and Visibility Manual for EU External Actions published by the European Commission: http://ec.europa.eu/europeaid/work/visibility/index_en.htm.

The contractor must cover transportation and installation of all visibility boards at the construction site.

The latest visibility requirements of the Interreg VI-A IPA Hungary-Serbia Programme must be respected for all contract obligations. The latest version of the VISUAL IDENTITY MANUAL & INFORMATION AND PUBLICITY GUIDELINES of the Interreg VI-A IPA Hungary-Serbia Programme is available at: https://hungary-serbia.eu/downloads.

Article 15	Performance guarantee

15.1	The amount of the performance guarantee will be 5 % of the amount of the contract and any addenda thereto.

Article 16	Liabilities and insurance

16.1 a)	The amount of insurance covering liability with regard to risks and civil liability insurance shall be in according with Article 16 of General Conditions.

Article 17	Programme of implementation of tasks

The Contractor shall submit to the Supervisor an Internal Implementation Programme in Critical            Path Analysis format within 14 days after the commencement of the works.

The programme shall reflect any specific requirements set out in the Contract Documents and Contractor's Tender, giving details on:

a)	the list of sub-contractors he proposes to employ on the Works together with 		details of the part of the Works he proposes to subcontract;

b)	the schedule of key personnel and organisation chart;

c)	the schedule of sources of materials, plant and equipment for incorporation into 		the works;

d)	milestones for all major groups of works etc. within the stated time for 			completion

e)	an approximate cash flow with monthly disbursement plan.

In the preparation of the Implementation Programme the Contractor shall take into account adverse weather conditions which may severely restrict progress in the winter months or during other wet periods of the year.  Programmes incorporating restricted working, or a temporary Suspension of Works shall be accepted by the Supervisor, but such acceptance shall not relieve the Contractor from his obligations under the Contract to complete the works in accordance with the agreed programme.

The Contractor’s Implementation Programme shall not, for any reason, exceed the overall contract period as stipulated in the Contract.  It shall only be revised and increased upon approval of an Addendum to the Contract.  Upon the written request by the Supervisor, the Programme and Schedule shall be updated by the Contractor and submitted to the Supervisor in hard copy and electronic format.

The Programme and Schedule shall be submitted in hard copy and electronic format. Programme shall take into account the appropriate time needed for purpose of informing public regarding closing the roads and streets or for limiting or disconnecting water, electricity or other utilities.

The Supervisor shall make comments and/or objections concerning the Programme and Schedule supplied by the Contractor within 10 calendar days of their submission. It shall be considered that all these comments and/or objections are accepted by the Contractor, if he should not contradict them in writing, either by registered letter, or fax sent to the Supervisor, within 7 calendar days of their receipt.

Programme of works:

The object No. 1 – demolition works, earthworks, masonry works, carpentry works, roofing and sheet metal works must be completed within 52 working days at the latest.

The object No. 2 – The demolition of the roof and interior walls must be completed within 72 working days at the latest.

The object No. 2 – Concrete and masonry works must be completed within 113 working days at the latest.

Object No. 2 – Carpentry and roofing work must be completed within 142 working days at the latest.

Interior works, exterior decoration and all craft works must be completed no later than the expiry of the agreed deadline, i.e. in the period from 142 to 272 working days.

Article 19	Contractor’s drawings and execution studies

19.1	On the basis of the Technical Specifications, Drawings and other information contained in the Tender Documents, the Contractor shall supply all further fabrication and other data necessary for the construction of the Works and for satisfying the technical parameters stipulated in the Contract. The Contractor may supply this information successively in parts, but each part submitted should be complete to such an extent that it can be judged and approved by the Supervisor in isolation as part of the whole.

The Supervisor may instruct the Contractor to prepare particular drawings or to make any modifications, including calculations for any part of the project. These calculations and drawings are part of the Contractor’s duties.

The Contractor shall prepare and keep up-to-date a complete set of As-Built records showing the precise locations, sizes and details of all the work executed. These records shall be kept on site and shall be used exclusively for this purpose. They shall be available to the Supervisor at any time. Hard copies shall be provided to the Supervisor when requested, in particular as evidence in support of Interim Payment Certificates. The absence of such records may lead to the Supervisor not forwarding submitted Interim Payment Certificates to the Contracting Authority.

The Contractor shall submit to the Supervisor As-Built drawings in a clear and easy-to-understand form, in one original of the reproducible negatives or drawings in electronic format, and two hard copies for each completed section of the works.

The works shall not be considered to be completed for the purpose of provisional acceptance until such drawings have been supplied to the Contracting Authority. Operation and maintenance manuals and As-Built drawings shall be handed over to the Supervisor not later than 14 days after provisional acceptance of the works. After revision, the Supervisor shall certify them or return them to the Contractor for correction and amendment.

19.7	The manuals and drawings shall be supplied in the language of the original with translation into English and Serbian Language, as instructed by the Supervisor.

Article 20	Sufficiency of tender prices

20.4	The contactor will calculate and present the amount for each item, based on the 			quantities of materials and works presented in the Volume 4 - Bill of Quantities.

The unit price for unforeseen works, to be recognized throughout the project and ordered 		by the Contracting Authority shall be derived from the Contract's Unit Prices of a same 		or similar type of works or extracted from referent recent similar contracts.

Throughout the construction of the Works the Contractor shall provide and maintain for 	the site staff appropriate offices, stores, dining rooms, sanitary and health and safety 	facilities etc. All operating and maintenance expenses connected therewith (lighting, 	heating, water supply etc.)  shall be borne by the Contractor. The Contractor may require 	land outside the Site for his offices, stores, workshops, fabrication plants etc. The 	expenses and other costs so incurred shall be at the expense of the Contractor.

20.5	The Contractor shall make his own arrangements for provision of water, electricity and telephones and shall observe all regulations of the appropriate local authority and shall bear all expenses in connection therewith.

Article 21	Exceptional risks

21.4	There are no exceptional risks other than specified in the General Conditions.

Article 24	Interference with traffic

24.1	No important operation of any kind, especially cutting through, transit over, or closing existing roads, water conduits or other public utility shall be carried out without the written consent of the Supervisor.

The Contractor shall inform the Supervisor in due time which shall be not less than 7 calendar days in writing before commencing such works in order that the Supervisor may arrange adequate supervision and safety precautions. With his application for permission to start construction work, the Contractor shall submit to the Supervisor a list of all major plant he and his sub-contractors intend to use, indicating their characteristics (Excavators, trucks, cranes, compaction equipment, rollers, concrete mixers, equipment, etc.).

The Contractor shall select routes, choose and use such vehicles and restrict and distribute loads in such a way to prevent damage to the roads or structures communicating with or on the routes to the Site.  The Contractor shall ensure that roads and bridges that have become damaged due to the Contractor’s use of that infrastructure, in the opinion of the Supervisor, are reinstated to a serviceability level similar to that which existed prior to the Contractor’s use of the infrastructure.

Reinstatement shall be to the approval of the Supervisor.  All expenses related to these procedures shall be covered by the Contractor.

The Contractor shall obtain any permission from the relevant authorities, which may be required to impede traffic on communication links, for his use of routes, signs and directions.

24.2	The Contractor will have to take necessary measures to secure the transportation of heavy loads and big size loads and/or any load on and around the site.

- the Contractor shall (as between the Parties) be responsible for any maintenance 		which may be required for his use of access routes;

- the Contractor shall provide all necessary signs or directions along access routes, 		and shall obtain any permission which may be required for his use of routes, signs 		and directions;

- the Contracting Authority and the Beneficiary shall not be responsible for any 		claims which may arise from the use or otherwise of any access route,

- the Contracting Authority and the Beneficiary do not guarantee the suitability or 		availability of particular access routes, and

Costs due to non-suitability or non-availability, for the use required by the Contractor, of access routes shall be borne by the Contractor

Article 27	Demolished materials

27.2	No material to be removed from the site as result of demolition, dislocations etc. will become the property of the Contracting Authority.

27.4	The contractor will be responsible for removal and disposal to the landfill of the demolition material.

Article 29	Temporary works

29.2	The Contracting Authority shall never be responsible for design of any particular temporary works, and temporary works shall always be resolved between the Supervisor and the Contractor.

Should the Contractor need any additional information or drawings apart from those being part of the Tender Dossier, he will put his request to the Supervisor/Beneficiary. Final decision will be on the side of the Supervisor.

Article 30	Soil studies

30.1	The Contractor shall make available to the Supervisor, the personnel and equipment necessary for carrying out any soil survey which the Supervisor considers reasonably necessary.  The Contractor shall bear all costs, without compensation, of the manpower and equipment used for any soil survey that may be necessary for the undisturbed project execution.

Article 32	Patents and licenses

32.1	There is no a derogation from Article 32 of the GC.

Article 34	Period of implementation of tasks

# 34.1	The period for execution of the Works shall be 13 (thirteen) months from the date of commencement date of the Works, but shall in any event not exceed 272 working days.

Article 36	Delays in the implementation of tasks

36.1	The rate of liquidated damages for delays in the completion of works shall be 0.1% of the contract price for every day or part thereof which elapses between the end of the period of implementation of tasks and the actual date of completion, up to a maximum amount of 10 % of the contract price or, if the contract is subdivided into phases, 10 % of the price of the phase concerned.

Article 39	Work register

39.1	A work register shall be kept in English and Serbian language. It will be kept on the site by the Contractor, who shall enter in it at least the following information:

(a) the weather conditions, interruptions of work owing to inclement weather, hours of work, number and type of workmen employed on the site, materials supplied, equipment in use, equipment not in working order, tests carried out in situ, samples dispatched, unforeseen circumstances, as well as orders given to the Contractor;

(b) detailed statements of all the quantitative and qualitative elements of the work done and the supplies delivered and used, capable of being checked on the site and relevant in calculating payments to be made to the Contractor

39.2	The statements shall be prepared by the Contractor, in accordance with the Specifications and the Bill of Quantities respectively. The statements shall be two separate documents, one for quality control and one for quantitative measurement. The documents shall be permanently kept at the site, in hard copy and in electronic format. The Contractor shall measure, in cooperation with the Supervisor’s staff, and prepare records of the work executed in such detail as instructed by the Supervisor.

Article 40	Origin and quality of works and materials

40.1	All goods purchased and materials under the contract may originate in any country.

## For these purposes, ‘origin’ means the place where the goods are mined, grown, produced or manufactured and/or from which services are provided. The origin of the goods must be determined according to the EU Customs Code or the applicable international agreement.

When importing goods, any change in the specified origin must be pointed out to the project supervisor and approved by him.

40.2	The works and the objects, appliances, equipment or materials used in their construction must comply with:

•	the requirements specified in Volume 3 (Technical Requirements).

•	the specifications as in Volume 4.

40.3	No preliminary technical acceptance is necessary.

Article 41	Inspection and testing

Inspection and testing shall be performed in accordance with the article 41 of GC and requirements of the applicable technical regulations and local legislations.

All materials and Equipment used are subject to inspection and testing by the Supervisor and Beneficiary and/or his substitutes at factory and on arrival at site.

The Contractor shall submit to Supervisor a schedule for factory tests to be performed during implementation of the project. The schedule must be approved by the Contracting Authority Representative/Supervisor and Beneficiary.

Article 43	Ownership of plant and materials

43.2	Equipment and materials intended for incorporation in the permanent works, but not yet incorporated in the permanent works and for which any interim payment has been made by the Contracting Authority, shall be vested in the Contracting Authority and visibly marked as such.

Article 44:	General principles for payments

44.1	Payments shall be made in the RSD for companies registered in Republic of Serbia or EUR for companies registered outside Republic of Serbia.

In case the contract is concluded in EURO, and payments are made in RSD, applicable exchange rate must be InforEuro exchange rate for the month of issuing of invoice.

44.2	There is no a derogation from Article 44.2 of the GC..

44.3	By derogation, pre-financing payment to the contractor for the lump-sum advance shall be made within 30 days. Other pre-financing payments to the contractor shall be made within 90 days. Interim payments to the contractor of the amounts due under each of the interim payment certificates approved by the supervisor shall be made within 45 days, and the final payment to the contractor of the amounts due after the final statement of account issued by the supervisor shall be made within 45 days.

Article 46	Pre-financing

46.1	No Pre-financing may be granted to the Contractor.

Article 47	Retention monies

47.1	The retentions from interim payments are not applicable. The amount of the retention guarantee will be 10 % of the amount of the contract and any addenda thereto.

Article 48	Price revision

Not applicable

Article 49	Measurement

49.1	This is a unit-price contract. No additions may be made to the items in the bill of quantities.

Article 50	Interim payments

50.1	Payments will be practically arranged in the following way:

At the beginning of each month during Contract implementation tenderer will compose report of temporary work situation. Report will be examined and approved by Supervisor and it will be used as base for interim payment request. In case that work finished have value of more than 5% of Contract value Contractor will then submit approved report with request for payment to Contracting Authority.

Article 51	Final statement of account

51.(1) and (2)

51.1	The contractor shall, submit to the supervisor a draft final statement of account when it applies for the final acceptance certificate. In order to enable the supervisor to prepare the final statement of account, the draft final statement of account is submitted with supporting documents showing in detail the value of the work done in accordance with the contract and all further sums which the contractor considers to be due to it under the contract.

51.2	Within 30 days from issuing the final acceptance certificate referred to in Article 62, the supervisor shall prepare and signed the final statement of account.

Article 59	Partial acceptance

59.3	The defects liability period provided for in Article 62 shall run from the date of the latest     Provisional Acceptance is signed.

Article 60	Provisional acceptance

60.1	In complement to article 60.1 of the General Conditions, as built design shall be submitted by the Contractor to the Supervisor before the Provisional Acceptance Certificate is issued by the Supervisor.

Article 61	Defects liability

61.1	The defects liability period is defined as the period commencing on the date of provisional acceptance, during which the contractor is required to make good any defect in, or damage to, any part of the work which may appear or occur during this period as notify by the supervisor or the contracting authority. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the general conditions.

61.6 	The normal wear and tear maintenance works shall not be borne by the Contractor.

61.7     The Defects Liability Period is 365 days.

Article 68	Dispute settlement

68.4	Any dispute arising out of or relating to this contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of relevant Court in Senta applying the national legislation of the Contracting Authority.

* * *